# SDP

# Software Development Plan

# Generic Program Comparator

# COP 4233 Fall 1998

# Instructor: Dr. Workman

# Creation Date:    24-SEP-98

# Last Update:    03-DEC-98

# Team 2 – The BYTE Girls

# Diana Griffith

# Bettina McCormick

# Stephanie Santiago

# Lavanya Vasudevan

# Table of Contents

## I.    Introduction

## A.    Summary of Contents

### Scope and Purpose

### System-level Description

### D.    Software Subsystem Description

## 1. Software Subsystem Description Update

## II. Resource & Schedule Estimates

### A.    Resource Profiles

1.    Function Point Investigation

2.    Feature Point Investigation

### B.    	Resource Profile Update 1

1.    Function Point Investigation

2.    Object-Method Estimation

3.    Brooks-Percentages Estimation

C.    Schedules

1. Proposed

## 2. Update 1

## III. Organization & Staffing

- Assigned Responsibilities

- Cost Accounting

IV. Work Breakdown Structure, Work Packages, Cost Accounts

V. Technical Management & Control

- Change Management

- Risk Containment

- Cost & Schedule Control

- Issue Resolution

VI. Standards & Procedures

- Development Methods

VII. Reviews, Audits, Walkthroughs

- Schedules

- Procedures/Criteria

- Responsibilities

VIII. Development Environment

IX. Technical Performance Measurement

## X.    Documentation

## XI. Verification & Validation

XII. Maintenance

XIII. Human Factors

XIV. Delivery, Installations & Acceptance

- Delivery

- Installations

- Acceptance

## XV.    Appendices & References

A.    Appendices

- Acronyms

2.    Glossary

B.    References

I.    Introduction

### A.    Summary of Contents

This Software Development Plan document describes in detail the software development plan for the software system to be developed.    This is a collaborative effort targeting the levels of quality, accuracy and integrity of the product needed by the client.    The goal of this document is to provide a baseline plan for the development process so that the best result is reached at the most satisfactory level in performance, time and efficiency.

### B.    Scope and Purpose

The scope of this document entails the System-level Description, Software Subsystem Description, Resource & Schedule Estimates, Organization & Staffing, Technical Management & Control, Standards & Procedures, Reviews, Audits, Walkthroughs, Development Environment, and Documentation.

The Plan described within is the result of a cumulative process that incorporates the views of this system from all possible user angles.    This process is not stagnant and singular, but continually evolving and coordinated throughout the development process.

### C.    System-level Description

The system to be developed is a generic program that will analyze (compare) two given programs, both written in Turbo Pascal programming language, to determine their “degree of similarity.”      Degree of similarity will be based on the number of occurrences of identical instances of certain pre-defined programming features (these are described in the glossary) appearing in a pair of programs being compared.    A visual description of this degree of similarity is illustrated in Figure 1. The GPC (Generic Program Comparator) must, as a minimum requirement, be able to detect that two programs are identical up to a renaming of variables.

A – B

32%

A Ç BX

35%            B – A

33%

B - AA

Program A

Program B

Program B

##### Figure 1 – Program Similarity

D.    Software Subsystem Description

Pascal Program Analyzer /

Feature Data Collector

Feature Data

1 .. n

Pascal Source Programs

1 .. n

Feature Data

1 .. n

Report

Feature Set

Feature Data Comparator /

Report Generator

Output Reports Generated

- Figure 2 – System Architecture

1.      Software Subsystem Description Update 1

Pascal Program Analyzer /

Feature Data Collector

2.0

PGM-A.PGM

(Feature Data)

Program-A

Pascal

Source Files

1 .. NI

A.NAME

(Name Table File)

library.SYM

(Pascal    Library Files)

Feature Data Comparator /

Report Generator

3.0

Pascal

Reserved

Words

Feature

Comparison

Reports (1..M)

for Programs

( A, B )

Pascal.SYM

(language definitions)

Pascal.NAME

(Name Table File)

Report

Feature Set

{1 .. M}

Program-B

Pascal

Source Files

1 .. NJ

B.NAME

(Name Table File)

Pascal Program Analyzer /

Feature Data Collector

2.0

PGM-B.PGM

(Feature Data)

Figure 2a – System Architecture Update

## II. Resource & Schedule Estimates

The primary goal in this development plan is to estimate the development time for this project and create a tentative, but realistic schedule to accomplish this plan.    The following sections, Resource Profiles and Schedules, began this process.    The process for the profiling our resources comes from the text, Software Engineering Fundamentals (see section XV, B.    References).

### A.    Resource Profiles

In order to profile our resources and determine a project estimation

we will investigate two methods: the Function Point and Feature Point methods.

In using both these methods, we drew our conclusions individually and then discussed the implications as a team to determine the merit and differences in our though process.    Then we decided upon a final approach to the estimation in each method.    The tables reflecting our individual reflections, as well as our final conclusion, are described in figures 3 –7 for the Function Point method and in figures 9 –13 for the Feature Point method:

1.    Function Point Investigation

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Bettina |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 2 | 3 |  |  |  |  | 6 |
| User Outputs | 1 |  |  |  | 7 |  | 7 |
| User Inquiries | 1 | 3 |  |  |  |  | 3 |
| Files | 5 |  |  | 10 |  |  | 50 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 66 |

Figure 3

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Lavanya |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 2 | 3 |  |  |  |  | 6 |
| User Outputs | 1 |  |  | 5 |  |  | 5 |
| User Inquiries | 1 |  |  | 4 |  |  | 4 |
| Files | 2 |  |  |  | 15 |  | 30 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 45 |

Figure 4

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Diana |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 2 | 3 |  |  |  |  | 6 |
| User Outputs | 1 |  |  |  | 7 |  | 7 |
| User Inquiries | 1 | 3 |  |  |  |  | 3 |
| Files | 2 |  |  |  | 15 |  | 30 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 46 |

Figure 5

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Stephanie |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 4 |  |  | 4 |  |  | 16 |
| User Outputs | 2 |  |  | 5 |  |  | 10 |
| User Inquiries | 0 |  |  |  |  |  | 0 |
| Files | 5 |  |  |  | 15 |  | 75 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 101 |

Figure 6

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Team Conclusion |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 2 |  |  |  | 6 |  | 12 |
| User Outputs | 1 |  |  |  | 7 |  | 7 |
| User Inquiries | 1 |  |  | 4 |  |  | 4 |
| Files | 2 |  |  |  | 15 |  | 30 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 53 |

Figure 7

The differences in our individual choices reflected a different view of what each category    meant and the complexity for each function.    Our conclusion reflects the team discussion and final decision concerning the function points.

From this point we determined our complexity factor (see figure 8), and then calculated the Adjusted Function Points (AFP):

AFP        =      53    x    [0.65    +    0.01 (8)]

AFP 	=      38.69	=      39

| Complexity Factor | Weight |
| --- | --- |
| 1: Backup & Recovery | 0 |
| 2: Data Communication | 0 |
| 3: Distributed Processing | 0 |
| 4: Critical Performance | 1 |
| 5: Heavily used Configuration | 0 |
| 6: On-line Data Entry | 0 |
| 7: Transaction Complexity | 0 |
| 8: On-line Master File Update | 0 |
| 9: Complex External Processing | 1 |
| 10: Complex Internal Processing | 4 |
| 11: Reusability | 2 |
| 12: Installation Factor | 0 |
| 13: Multiple Sites | 0 |
| 14: Change Facilitation | 0 |

Total:		8                                    Figure 8

We multiply this AFP by the coefficient of the source lines of code (SLOC) for the development language we will be using (C coefficient = 120 / FP) to determine the total SLOC for the project:

SLOC    =    39 x 120    =      4680 sloc

Now to determine the translation of this quantity of SLOC into time in labor months, we use the COCOMO model (Chapter 15 of text referenced for this section).    The profile of our team lies between the Organic (Small number of experienced developers who are familiar with both the application area and the development environment.    Product size varies from small to medium.) and the Semi-Detached (Assumes the development team is a mix of experienced and inexperienced personnel with little experience working together.      Product size varies from medium to very large.) development modes.    So we can determine a lower and upper bound for the time frame of this project in labor months (LM) and development time (DT):

Lower bound:

LM    =    2.4    x    (KSLOC) 1.05

LM    =    11.9    ~ 12 labor months

DT    =    2.5 (LM) 0.38

DT    =    6.4

Upper bound:

LM    =    3.0    x    (KSLOC) 1.12

LM    =    16.6    ~ 16 labor months and 2 weeks

DT    =    2.5 (LM) 0.35

DT    =    6.7

The labor months effect our cost structure and the development time is pertinent to our schedule.

2.    Feature Point Investigation

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Stephanie |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | COMPLEXITY RANK |  |  |  |  |  |  |
| Feature Attributes | Count |  | Low |  |  | Ave |  | High |  |  | Feature Points |
| User Inputs | 2 |  |  |  |  | 4 |  |  |  |  | 8 |
| User Outputs | 2 |  |  |  |  | 5 |  |  |  |  | 10 |
| User Inquiries | 0 |  |  |  |  |  |  |  |  |  | 0 |
| Files | 2 |  | 3 |  |  |  |  |  |  |  | 6 |
| External Interfaces | 0 |  |  |  |  |  |  |  |  |  | 0 |
| Algorithms |  | 5 |  |  |  |  |  |  | 6 |  | 30 |
| TOTAL FP (TFP) |  |  |  |  |  |  |  |  |  |  | 54 |

Figure 9

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Bettina |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | COMPLEXITY RANK |  |  |  |  |  |  |
| Feature Attributes | Count |  | Low |  |  | Ave |  | High |  |  | Feature Points |
| User Inputs | 2 |  |  |  |  | 4 |  |  |  |  | 8 |
| User Outputs | 1 |  |  |  |  |  |  | 7 |  |  | 7 |
| User Inquiries | 2 |  | 3 |  |  |  |  |  |  |  | 6 |
| Files | 1 |  |  |  |  |  |  | 7 |  |  | 7 |
| External Interfaces | 0 |  |  |  |  |  |  |  |  |  | 0 |
| Algorithms |  | 4 |  |  |  |  |  |  | 6 |  | 24 |
| TOTAL FP (TFP) |  |  |  |  |  |  |  |  |  |  | 52 |

Figure 10

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Diana |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | COMPLEXITY RANK |  |  |  |  |  |  |
| Feature Attributes | Count |  | Low |  |  | Ave |  | High |  |  | Feature Points |
| User Inputs | 3 |  | 3 |  |  |  |  |  |  |  | 9 |
| User Outputs | 2 |  |  |  |  | 5 |  |  |  |  | 10 |
| User Inquiries | 1 |  | 3 |  |  |  |  |  |  |  | 3 |
| Files | 2 |  | 3 |  |  |  |  |  |  |  | 6 |
| External Interfaces | 1 |  |  |  |  |  |  | 7 |  |  | 7 |
| Algorithms |  | 4 |  | 3 |  |  |  |  |  |  | 12 |
| TOTAL FP (TFP) |  |  |  |  |  |  |  |  |  |  | 47 |

Figure 11

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Lavanya |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | COMPLEXITY RANK |  |  |  |  |  |  |
| Feature Attributes | Count |  | Low |  |  | Ave |  | High |  |  | Feature Points |
| User Inputs | 2 |  |  |  |  | 4 |  |  |  |  | 8 |
| User Outputs | 1 |  |  |  |  |  |  | 7 |  |  | 7 |
| User Inquiries | 2 |  | 3 |  |  |  |  |  |  |  | 6 |
| Files | 5 |  |  |  |  |  |  | 7 |  |  | 35 |
| External Interfaces |  |  |  |  |  |  |  |  |  |  | 0 |
| Algorithms |  | 2 |  |  |  |  |  |  | 6 |  | 12 |
| TOTAL FP (TFP) |  |  |  |  |  |  |  |  |  |  | 68 |

Figure 12

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  |  |  |  |  | Date 9/24/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Team Conclusion |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | COMPLEXITY RANK |  |  |  |  |  |  |
| Feature Attributes | Count |  | Low |  |  | Ave |  | High |  |  | Feature Points |
| User Inputs | 2 |  |  |  |  | 4 |  |  |  |  | 8 |
| User Outputs | 1 |  |  |  |  |  |  | 7 |  |  | 7 |
| User Inquiries | 1 |  | 3 |  |  |  |  |  |  |  | 3 |
| Files | 2 |  |  |  |  |  |  | 7 |  |  | 14 |
| External Interfaces |  |  |  |  |  |  |  |  |  |  | 0 |
| Algorithms |  | 3 |  |  |  |  |  |  | 6 |  | 18 |
| TOTAL FP (TFP) |  |  |  |  |  |  |  |  |  |  | 50 |

Figure 13

With the Feature Point method we used another approach to the complexity issue and determined the Logical Complexity Value (LCV) and the Data Complexity Value (DCV)    to get our Adjustment Multiplier:

LCV    +    DCV    =    4 + 3    =    7

Adjustment Multiplier    =    1.1

Then we used this value to obtain our AFP:

AFP      =    50    x    1.1    =    55

SLOC = 55 x 120    =    6600

The translation process is the same as before:

Lower bound:

LM    =    2.4    x    (KSLOC) 1.05

LM    =    17.4      ~ 17 labor months and 2 weeks

DT    =    2.5 (LM) 0.38

DT    =    7.4

Upper bound:

LM    =    3.0    x    (KSLOC) 1.12

LM    =    24.8    ~ 24 labor months and 3 weeks

DT    =    2.5 (LM) 0.35

DT    =    7.7

The labor months effect our cost structure and the development time is pertinent to our schedule.

B.    Resource Profile Update 1

1.    Function Point Investigation

In using the Function Point method, we drew our conclusions individually and then discussed the implications as a team to determine the merit and differences in our though process.    Then we decided upon a final approach to the estimation in each method.    The tables reflecting our individual reflections, as well as our final conclusion, are described in figures 14 –18 for the Function Point method.

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 11/18/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Bettina |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 4 | 3 |  |  |  |  | 12 |
| User Outputs | 1 |  |  | 5 |  |  | 5 |
| User Inquiries | 1 | 3 |  |  |  |  | 3 |
| Files | 1 |  |  | 10 |  |  | 10 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 30 |

Figure 14

| Unit/Module Name SDP – Generic Program Comparator |  |  |  |  |  | Date 11/18/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Lavanya |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 4 |  |  | 4 |  |  | 4 |
| User Outputs | 1 |  |  |  | 7 |  | 7 |
| User Inquiries | 3 |  |  | 4 |  |  | 12 |
| Files | 1 |  |  | 10 |  |  | 10 |
| External Interfaces | 1 |  |  | 7 |  |  | 7 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 40 |

Figure 15

| Unit/Module Name Program Analyser 1.0 |  |  |  |  |  | Date 11/18/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Diana |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 1 | 3 |  |  |  |  | 3 |
| User Outputs | 0 |  |  |  |  |  | 0 |
| User Inquiries | 1 |  |  | 4 |  |  | 4 |
| Files | 2 |  |  | 10 |  |  | 20 |
| External Interfaces | 1 | 5 |  |  |  |  | 5 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 33 |

Figure 16

| Unit/Module Name Program Analyser 1.0 |  |  |  |  |  | Date 11/18/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Stephanie |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 7 | 3 |  |  |  |  | 21 |
| User Outputs | 1 | 4 |  |  |  |  | 4 |
| User Inquiries | 3 |  |  |  | 6 |  | 18 |
| Files | 8 | 7 |  |  |  |  | 56 |
| External Interfaces | 0 | 5 |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 99 |

Figure 17

| Unit/Module Name Program Analyser 1.0 |  |  |  |  |  | Date 11/18/98 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team # 2 | Team Member Name: Team Conclusion |  |  |  |  |  |  |
|  |  |  | COMPLEXITY RANK |  |  |  |  |
| Attributes | Count | Low |  | Ave | High |  | Function Points |
| User Inputs | 4 | 3 |  |  |  |  | 12 |
| User Outputs | 1 |  |  | 5 |  |  | 5 |
| User Inquiries | 2 | 3 |  |  |  |  | 6 |
| Files | 2 | 7 |  |  |  |  | 14 |
| External Interfaces | 0 |  |  |  |  |  | 0 |
| TOTAL FP (TFP) |  |  |  |  |  |  | 37 |

Figure 18

The differences in our individual choices reflected a different view of what each category meant and the complexity for each function.    Our conclusion reflects the team discussion and final decision concerning the function points.

From this point we determined our complexity factor (see figure 19), and then calculated the Adjusted Function Points (AFP):

AFP        =      37    x    [0.65    +    0.01 (8)]

AFP 	=      27.01	=      27

| Complexity Factor | Weight |
| --- | --- |
| 1: Backup & Recovery | 0 |
| 2: Data Communication | 0 |
| 3: Distributed Processing | 0 |
| 4: Critical Performance | 1 |
| 5: Heavily used Configuration | 0 |
| 6: On-line Data Entry | 0 |
| 7: Transaction Complexity | 0 |
| 8: On-line Master File Update | 0 |
| 9: Complex External Processing | 1 |
| 10: Complex Internal Processing | 4 |
| 11: Reusability | 2 |
| 12: Installation Factor | 0 |
| 13: Multiple Sites | 0 |
| 14: Change Facilitation | 0 |

Total:		8		Figure 19

We multiply this AFP by the coefficient of the source lines of code (SLOC) for the development language we will be using (C coefficient = 120 / FP) to determine the total SLOC for the project:

SLOC    =    27 x 120    =      3240 sloc

Now to determine the translation of this quantity of SLOC into time in labor months, we use the COCOMO model (Chapter 15 of text referenced for this section).    The profile of our team lies between the Organic (Small number of experienced developers who are familiar with both the application area and the development environment.    Product size varies from small to medium.) and the Semi-Detached (Assumes the development team is a mix of experienced and inexperienced personnel with little experience working together.      Product size varies from medium to very large.) development modes.    So we can determine a lower and upper bound for the time frame of this project in labor months (LM) and development time (DT):

Lower bound:

LM    =    2.4    x    (KSLOC) 1.05

LM    =    8.1    ~ 8 labor months

DT    =    2.5 (LM) 0.38

DT    =    5.5

Upper bound:

LM    =    3.0    x    (KSLOC) 1.12

LM    =    10.8    ~ 10 labor months and 3 weeks

DT    =    2.5 (LM) 0.35

DT    =    5.7

The labor months effect our cost structure and the development time is pertinent to our schedule.

2.    Object-Method Estimation

The Object-Method Estimation uses the objects we have thus far determined and an estimation of how many lines of code it would take to write the methods for each object.

# Bettina’s SLOC

Lexer

declations					10

Get Token					250

(DFA for parsing                n search

Call token 		n search)

Init_lexer 					40    								                                                                      ----------------------

300 lines

## File

Open 		simple				10

Close 		simple				10

Read 		simple 			10

Write 		simple 			10

Create	simple 			20

---------------------

60 lines

## Sym_ref

## declarations					10

Create 	simple 			20

Start_is 	simple 			10

Stop_is 	simple 			10

Set_start	simple    			10

Set_stop	simple				10

---------------------										70 lines

## Symbol

## declarations					10

## Create 	simple				20

Set_frame	simple 			10

Add_ref	simple				15

Id_is		simple				10

Cat_is		simple	 			10

Type_is	simple				10

Ref_is		simple				10

Frame_idis	simple				10

Printref_list	simple				15

---------------------

120 lines

## Total:    120 + 300 + 60 + 70 = 550 SLOC

#### Diana’s SLOC

##### Stack

Create	simple				10

Push		simple				10

Pop		simple 			10

Top		simple				10

Empty 	simple				10

---------------------											50 lines

Parse_stk						20 lines

Frame_stk						20 lines

##### Tokens

Create_token				10

Id_is						10

Cat_is						10

Reference_is					10

Value_is					10

Set_reference				10

Set_category					20

Set_id						10

Set_value					10

---------------------

100 lines

##### Frames

Create					20

Add_sym					15

Find_sym					50

Output					75

Search					20

---------------------

180 lines

##### Total:    180 + 100 + 150 + 20 + 20 = 370 SLOC

#### Stephanie’s SLOC

##### Parser

Go() – extra difficult

(resolve ident, comment, literals)	300

load RSW table, uses table	    	25

manipulate objects		 	    	75

make sys_files				100

---------------------											500 lines

##### List

Create_list	easy				10

Add		easy 				10

Remove	easy				10

Size_of	easy				10

Last_elt	easy				10

First_elt	easy				10

---------------------

60 lines

##### Ref_list

Same methods as list 			0

Implementation/ variables			20

---------------------

20 lines

##### Total: 20 + 60 + 500 = 580 SLOC

# Lavanya’s SLOC

User_main		    		 		25 lines

Outputter						100 lines

Rswd_table

declarations					10

Load						10

Find						10

---------------------				    							30 lines

Uses_table

declarations					20

Init						10

Add_frame					15

Searches					15

---------------------											60 lines

Filename_table

declarations					15

Load						10

Empty						12

Next						10

Reset						15

---------------------											62 lines

##### Name_table

##### declations					15

Init						10

Find						20

Insert						16

Create					10

Load						10

Output					10

---------------------											76 lines

##### Total:      76 + 62 + 25 + 100 + 30 + 60      = 368 SLOC

# Totals

Bettina 		550

Diana			370

Stephanie		580

Lavanya 		368

------

1868 SLOC

This estimation is probably lower than our actual code, due to the fact that we haven’t investigated all the methods needed by each object. This will be more apparent when we complete the Dynamic model.

3.    Brooks-Percentages Estimation

The Brooks-Percentages Estimation looks at the time our team has actually spent on the design portion of this project through our projected Presentation date and determines what percentage that portion represents using the percentages suggested by Fred Brooks.    This then leaves us with the remaining percentage to complete the project – and thus, we can determine an estimation of the time it will take the next team to pick up our design and complete this project.    This method may prove most useful for an independent study classmate to predict their time investment and to estimate what percentage of the project is possible to complete in one semester.

Fred Brooks stated, “My rule of thumb is 1/3 of the schedule for design, 1/6 for coding, 1/4 for component testing, and 1/4 for system testing.” (The Axioms of Estimation (Fred Brooks, “The Mythical Man-Month”, 1975.

Team 2 completed the design phase (1/3 of the schedule) in the course of one semester.    The total time spent was 616.75 hours.    Following the Brooks-Percentages Estimation,    the remaining time to complete the project (2/3 of the schedule) is 1252.00 hours.

Considering a 16 week semester, one person would have to average:

· 78.25 hours per week to complete the entire project

· 18.25 hours per week to complete the coding only

· 30 hours per week to complete the component testing only · 30 hours per week to complete the system testing only

A team of four would have to average 19.5 hours per week in order to complete the entire project.

C.    Schedule

## Proposed

Figure 20 reflects the Proposed Project Manager general schedule for this project.    This will undergo some changes as our estimations have predicted a longer development time.    Chapter 15 of the text referenced goes into further detail regarding the percentages of time to be spent in each phase.

Figure 21 reflects a more detailed schedule for the next phase, Requirements Analysis(OOA).    This is a crucial phase in the understanding of the process and has a great impact on the completion of this project and the process of change throughout to project.

| PHASE/TASK | 4-Oct | 11-Oct | 18-Oct | 25-Oct | 1-Nov | 8-Nov | 15-Nov | 22-Nov | 29-NOV | 6-Dec | 13-Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Analysis(OOA) |  |  |  |  |  |  |  |  |  |  |  |
| SW Architecture Design | ****** | ******* | ******* | ******** |  |  |  |  |  |  |  |
| Preliminary Design Review |  |  | PDR |  |  |  |  |  |  |  |  |
| Baseline Architecture(SDS) |  |  |  | Due |  |  |  |  |  |  |  |
| Detailed Design |  |  |  |  |  |  |  |  |  |  |  |
| Code and Unit Test |  |  |  |  |  |  |  |  |  |  |  |
| Integration and Test |  |  |  |  |  |  |  |  |  |  |  |
| System Acceptance & Delivery |  |  |  |  |  |  |  |  |  |  |  |

Figure 20

Goals: 10/4

- study object-oriented design approach

- assess project individually and determine objects and classes and OOD

- meet to blend individual ideas of design

- assign responsibilities of this phase and begin individual work

Goals: 10/11

-schedule preliminary design review with Client - Thursday Oct 8

- prepare SW Architecture

- develop system to track changes

Goals: 10/18

- get feedback from preliminary design review

- revise SW Architecture

- prepare for formal Review and schedule with Client - Tuesday Oct 20

Goals: 10/25

- Tuesday Oct 20 - Formal review and feedback

- complete last changes

- submit baseline architecture

## Figure 21

## 2.    Update 1

Figure 22 reflects    our daily schedule after our updates time estimations:

Daily Schedule for the Rest of the Semester

Team 2- Byte Girls - Nov 19, 1998

19-NOV	THU	Class Time- Guest Lecture

4:00 - 5:15    Project Manager Meeting - Discussion of Wednesday's Team-Meeting Decisions.

Discussion of the Dynamic Model

Discussion of possible Revision to Object Model - Missing

Object?

Can we meet this Saturday (21) and Wednesday morning 25)???	(NO)			(YES)

20-NOV	FRI	Individual Work in assigned activities.

Lavanya 	Dynamic Model

Update SRS

Diana            	Object Model

Schedule

Weekly's Update

Bettina     	Time Estimations

Update SDP

Functional Model (Done)

Stephanie	Time Estimations

21-NOV	SAT        Meeting with PM. from 9:00 - 12:00 for Dynamic Model.

22-NOV	SUN

23-NOV	MON      Team Meeting from 3:00 - 4:00 to discuss    Test Plan and

Integration.

24-NOV	TUE	SDP and SRS Updated, completed and Uploaded.

Meeting (1 hour) during or after class to discuss Testing Plan

(be prepared!!!)

25-NOV 	WEN	Team Meeting with PM (pos. 9:00-12:00 or early in the morning)

FINALIZE dynamic models.

Any question about the test plan.

26-NOV	THU	TURKEY DAY -- HAPPY THANKSGIVING    DAY

27-NOV	FRI	LEFTOVER DAY

28-NOV	SAT	RECOVER FROM SO MUCH TURKEY - DAY!!!!

29-NOV	SUN

30-NOV	MON	- Progress Update Meeting.

Review our latest dynamic model.

Review Test Plan Project.

01-DEC	TUE	- TBD

02-DEC	WEN	- Power Meeting from 1:00-4:00.

REVISE ALL MODEL ALL DOCUMENTATION...

How far along are we?

Documentation: 	SRS - SDP

ALL MODELS

TEST PLAN & INTEGRATION

PRESENTATION SAMPLE PROGRAM.

03-DEC	THU	- Meeting 4:00-5:00, PM. Preview- Preparing for Presentation.

Request Room Availability.

04-DEC	FRI	- TBD

05-DEC	SAT	- DRY-RUN.

FINAL

WEEK.	07-DEC to 11-DEC	TUE/THU------>    FORMAL PRESENTATIONS.

WE MADE IT!!!

Figure 21

## III. Organization & Staffing

A.    Assigned Responsibilities

Given the resources required and schedule estimates (section II of SDP) for each software development product the following will determine the organization and staffing to perform this development:

Experienced Project Manager: Dr. David Workman.

Technical Staff Assistant: Diana G. Griffith

Protocol Team/ Organizational Unit - Lavanya Vasudevan - Team Engineer in charge of database problems.    Responsible for collecting all data definitions, maintaining SDP changes and updates distributions.    In charge of recording changes to requirements, problems and how to get them solved. Also in charge of recording and getting approval of classes and object changes.

Requirement Analysis. (OOA) Responsibilities:

A great part of the Requirement Analysis (OOA) will be focused on object modeling, which represents the static, structural, “data” and functionality aspects of the system.

Functional Model - Bettina McCormick - Team Engineer responsible    for what happens, when and where using data flow diagrams.

Object Model - Stephanie Santiago- Team Engineer in charge of describing the structure of objects in the system.

Dynamic Model - Lavanya Vasudevan - Team Engineer in charge of describing aspects of the systems.    Each and every possible event concern with time and changes.

Event Traces, Scenarios and State Changes - Diana Griffith - Team Engineer in charge of the part of the dynamic model responsible for modeling a sequence of events, and determine diagrams that capture each scenario.

Schedule of when each part of the project has to be completed for reviews are established in the resource and schedule estimate section (II).    Each team engineer is in charge of following time schedule specifications for their units, and getting team 2 members to achieve the final product of the Requirement Analysis.

B.    Cost Accounting (N/A)

- Work Breakdown Structure, Work Packages, Cost Accounts (N/A)

- Technical Management & Control

A.    Change Management

An up-to-data document implies a well organized group of software developers who can assure faster deliverables and an efficient system.    These tasks can be achieved if changes in a document are maintained regularly and in detail.    Efficient updating and reduction in testing time are some of the advantages of change management.    The required details to an effective documentation of changes are:

1. Description of the change

2. How it was implemented? Justification?

3. The areas that will be have an impact due to the change

4.    and where, when(date and time) and by whom(team) was the change made?

The following are two forms for documenting changes.

Form A helps document the changes to the Requirement Specifications.

Form B helps document the changes to the Object/Class interfaces.

Form A: Changes to Requirements Specifications

Team:

Date:

Time:

Description of Change:

Why the change:

How was the change implemented:

What components are affected:

Who made the changes:

Form B: Changes to Object/Class Interfaces:

Team:

Date:

Time:

Circle the desired answer:

Description of Change (Object / Class):

Why the change: (Object/Class)

How was the change implemented: (Object/Class)

What components are affected: (Object/Class)

Who made the changes:

B.    Risk Containment

Weekly Reports! Will be used to document and track problems and manage risk.

C.    Cost and Schedule Control

Weekly Reports! Will be used to document and track problems and manage risk.

D.    Issues Resolution

Weekly Reports! Will be used to document and track problems and manage risk.

VI.    Standards and Procedures

- Shall follow source code commenting and style convention.

- Follow COA/OOD Methodology and SWDLC as prescribed in class (COP 4233 Fall 98)

- Use UML as the notation for documenting Software design

- Use ANSI C programming language

VII. Reviews, Audits, Walkthroughs

A.    Schedules

- SRR - Software Requirement Review - Date: N/A

- PDR - Preliminary Design Review - Date: 10/8

- CDR - Critical Design Review - Date: 10/20

B.    Procedures/Criteria

We are going to use object modeling techniques in the development of our system. We will have one formal review in which the acceptance criteria is the following:

1.    entrance criteria:

- Have a complete definition of Input / Output

- Identification of Global variables

- Complete Object, Dynamic and Functional Models, with all the appropriate requirements.

- Complete documentation.

2.      exit criteria:

- All review issues must be solved or established to the satisfaction of the review team.

D.    Responsibilities

Preliminary design review will be held on the week of October 18.    Weekly meeting with project manager will ensure constant inspection of the development process as informal reviews of each team engineer responsibilities.

VIII. Development Environment

- Environmental Limitations

- Windows 95 or higher

- Windows NT    4.0 or higher

- IBM compatible machines. (Room CCII 201)

B. Compliance with standards

- Shall follow source code commenting and style conventions

- Follow COA/OOD Methodology and SWDLC as prescribed in class (COP 4233      Fall 1998)

- Use UML as the notation for documenting Software design

- Use ANSI C programming language

IX. Technical Performance Measurement. (N/A)

X.    Documentation

The documentation process entails separation of the responsibilities of different sections to different members of the team.    One person from the team will be responsible for the maintenance and changes to each document and these responsibilities are noted under the References section of each document.      This process should ensure a balance of responsibilities as well as accountability and a way of tracking changes to the documentation as the development progresses.

Documentation for this document and all documentation throughout this project will be created with Microsoft Office ’97:    Word, Excel, Power Point and Access.

The standards for creation of individual sections are: no tabs, bullets, italics or bolding of headers; all text is to be left aligned with a default font Arial, 12pt;.    This will enable the team member responsible for merging each document to be able to format all sections with minimal rewriting or reformatting.

## XI. Verification & Validation (TBD)

XII. Maintenance (N/A)

XIII. Human Factors (N/A)

XIV. Delivery, Installations & Acceptance

A. Delivery

All deliverable design code and test documents shall be up to date and shall reflect the software system as defined by the acceptance tests.    The source code for the Generic Program Comparator shall belong solely to the client.

B. Installations

N/A

C. Acceptance

The Generic Program Comparator (GPC) must successfully report a degree of similarity between feature data among two programs written in Pascal.    The mission requirement is to generate a successful report. The GPC should be completed by December 13, 1998 with all its components working and tested with passing results (Closure Date).    These include:

1.    Verification that the software was developed accordingly to the functional requirements (section 3.1 of the Software Requirements Specification (SRS)), External Interface requirements (section 3.2 of the SRS), Performance requirements (section 3.3 of the SRS) and under the established Design Constrains (section 3.4 of the SRS).

2.    Validation that the requirements satisfy client and customer need.

- No training and/or installation will be needed for the acceptance criteria.

A Formal Acceptance Criteria, for each module, will be stated such that testing can be determined and assembled with the developing process.

## XV.    Appendices & References

A.    Appendices

1.    Acronyms

GPC – Generic Program Comparator SDP – Software Development Plan

- Use Case – model describing the user/system interaction for a traceable function

- PPA/FDC - Pascal Program Analyzer / Feature    Data Collector

- FFDC/FRG - Feature Data Comparator / Feature Report Generator

- RTC - Requirement Tracebility Matrix

- FP -    function points

- AFP – adjusted function points

- SLOC - source lines of code

COCOMO -    COnstructive COst MOdels

LM – Labor Months

DT – Development Time

2.    Glossary

Build: Building a system by collection of threads.

Configuration Control: Software modules can not be changed with out formal reviews and concurrence from all major team developers and program manager.

Feature:    A lexical element of a source program, such as variable names, comments, etc.

Maximal Feature Set:    The set of features for which the Program Analyzer will collect data:

{ comments, constants, function names, library names, literals, parameter

names, procedure names, reserved words, type names, unit names,

variable names    }

Module: Logical separate part of a program.    Components and Units are used interchangeably.

Report Feature Set:    (a subset of the Maximal Feature Set) The set of features for which the Feature Report Generator will report the data collected.

Software Validation: All actions at the end of the development that indicate that the software product has bee built correctly reflecting the SRS or its equivalent.

Software Verification: All actions taken at the end of a given development phase that confirms the software has been built correctly and satisfies condition imposed at the beginning of the developmental phase.

String or Thread: A collection of modules that together with support of other modules carry out one or more major system functions that can be exercised independently.

B.    References

The efforts of many individuals are woven into the production of this document and an attempt to enumerate these individuals and other resources vital to this collaborative effort will be made.

Dr. David Workman – Project Manager: Provided training, resources and structure for the development process.

Diana Griffith – Team Lead: Point of contact for project manager, coordinated team meetings, facilitated communication and assigned work and responsibilities.    Authored sections III and VII of this document.

Bettina McCormick – Team Engineer:    Authored sections I, II, X and XV of this document and all updates.

Stephanie Santiago – Team Engineer: Integrated all the sections into the final whole and proof read this document.

Lavanya Vasudevan – Team Engineer: Authored sections V and VI of this document.

Software Engineering Fundamentals, by Behforooz and Hudson, Oxford Press, 1996;    ISBN 0-19-510539-7.

UML Distilled: Applying the Standard Object Modeling Language, by Martin Fowler with K. Scott, Addison-Wesley, 1997;

ISBN = 0-201-32563-2.